# Quickstart

- As an organizer (even if you were previously an MLOps Community Organizer), please fill in the intake form.

- READ THIS Playbook for organizers thoroughly,

- Chapter Folder can be found here. Each should contain,

  - Event Tracker (for you to keep track of events, and tasks for each)

  - Banners (for the luma and chapter pages)

  - <Event Folder>

    - Slides for the day of the event

    - Slides for banners and sharing on LinkedIn

    - [optional] Attendee CRM (To keep track and notes)

    - AI writing prompts now live as Claude skills (the AAIF meetup skills repo), not in this folder

- PLEASE UPDATE THESE FOR YOUR CHAPTER

- Luma Event to clone (please ping ijeoma to be added as organizer so that you can clone it. NOTE: this event has form to fill and a terms the attendees need to accept)

  - When you clone an event, please add AAIF Community as host so we can track the event.

  - Create a tab in your event tracker doc.

- Templates Folder (Will have latest shared templates)

- Link to share with people who want to host, speak, or become organizers. 
NOTE : Each of these has special guidelines that they need to agree to.

  - It adds to our "database" (which is a Google Sheet for now) and allows us to track, approve, and also reach out to them for future events.

  - All the guidelines for people looking to get involved are here:

    - Organizers

    - Speakser

    - Venue Hosts

    - Collaborators

    - Attendees

    - Paid Venues

How to use this tracker - One event = one section = one Google Docs tab. The example below is your starting point — copy it and edit in place. - Fill the details first. The Luma URL is the source of truth for date, time, and RSVPs. - Each phase is a table: set the Owner, a Due date, and move Status from Not started → In progress → Done. - Words, prompts, and branding assets (Day-of slides, Luma banner, LinkedIn carousel, logo) live in the shared Resources & Templates doc.

AGENTIC AI FOUNDATION · COMMUNITY SERIES

# San Francisco

Self-organizing playbook for the series and its events

## About the AAIF San Francisco

The AAIF San Francisco is a recurring, vendor-neutral online series. [Describe the format, cadence, and focus of this series here — what you read or discuss, who it's for, and how often it runs.]

## Series Vibes

Our events are built for builders. We prioritize signal over noise, focusing on technical deep dives, practical demos, and honest conversations about what works in production. It’s an intimate, curated, and vendor-neutral space where the community gathers to share real artifacts, solve hard problems together, and build the future of agentic AI in real time.

## Organizers

- Rahul Parundekar

- Arthur Coleman

- Leo Walker

- Shreeganesh Ramanan (SG)

## Luma & Socials

- https://luma.com/aaif-sanfrancisco

# June 24, 2026  ·  AGENTIC AI NIGHT — LAUNCH SERIES

Example event — duplicate this whole section per night and overwrite the details.

| EVENT TITLE | Agentic AI Night · Launch Series |
| --- | --- |
| DATE & TIME | Tue · June 24, 2026 · 17:30 — late |
| PLATFORM | Online — attendees join from anywhere |
| STREAM / JOIN LINK | Zoom / Luma stream — join link sent to RSVPs |
| THEME / SERIES | Agents in production (Launch Series) |
| FORMAT(S) | Talk / Panel / Science Fair / Hackathon / Pitch Night / Workshop / Show & Tell / etc. |
| SPEAKER(S) | Maya Chen (Staff Eng · Payments); Diego Alvarez (Founding Eng · Agent Infra); Priya Nair (OSS · goose) |
| LUMA URL | lu.ma/aaif-sanfrancisco |
| CAPACITY / RSVPS | 120 · curated, RSVP-based |
| ORGANIZER ON POINT | Organizer Name (co: Organizer Name) |

## 4 WEEKS OUT   May 27 · lock the basics

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Confirm date, time zone, and the streaming platform | Organizer | May 27 | Done |
| Decide the theme / series and capacity | Local champs | May 27 | Done |
| Confirm speakers + talk titles and one-line abstracts | Organizer | May 27 | Done |
| Draft the event description (Resources → Luma prompt) | Co-organizer | May 29 | Not started |
| Create the Luma event (draft); set cover (AAIF Luma Banners) | Co-organizer | May 29 | In progress |

## 3 WEEKS OUT   Jun 3 · open RSVPs & announce

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Publish the Luma event; turn on the waitlist | Co-organizer | Jun 3 | Not started |
| Finalize headshots, bios, talk titles (Resources → bio prompt) | Organizer | Jun 4 | Not started |
| Post the LinkedIn announcement + carousel | Co-organizer | Jun 4 | Not started |
| Ask speakers to reshare | Organizer | Jun 5 | Not started |
| Tech check with speakers (screen share, audio, camera) | Host | Jun 6 | Not started |

## 2 WEEKS OUT   Jun 10 · logistics

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Confirm the run-of-show and segment timings | Host | Jun 10 | Not started |
| Assign someone to capture screenshots / clips | Co-organizer | Jun 10 | Not started |
| Prep slides, holding screen, and a shared chat / notes doc | Organizer | Jun 11 | Not started |
| Send reminder #1 to RSVPs (Resources → reminder prompt) | Co-organizer | Jun 11 | Not started |
| Line up a co-host to moderate chat / Q&A | Organizer | Jun 12 | Not started |

## 1 WEEK OUT   Jun 17 · final prep

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Re-confirm speakers: slide format, demo, screen-share & connection | Organizer | Jun 17 | Not started |
| Re-confirm the join link, backup host, and recording setup | Host | Jun 17 | Not started |
| Finalize run-of-show / agenda with timings | Organizer | Jun 18 | Not started |
| Build the day-of slides (AAIF SF Day of Event) | Co-organizer | Jun 19 | Not started |
| Send reminder #2 + calendar add to RSVPs | Co-organizer | Jun 20 | Not started |

## DAY BEFORE   Jun 23

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Export the RSVP list; confirm everyone has the join link | Organizer | Jun 23 | Not started |
| Prep slides, holding screen, speaker-timings note | Co-organizer | Jun 23 | Not started |
| Test mic, camera, and screen share on the host machine | Co-organizer | Jun 23 | Not started |
| Prep backups: stable connection, second device, headphones, charger | Organizer | Jun 23 | Not started |
| Confirm who opens the room / starts the stream, and when | Organizer | Jun 23 | Not started |

## DAY OF   Jun 24 · setup runbook

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Host opens the room early, on point | Organizer | 16:00 | Not started |
| Open the meeting room; enable the waiting room | Host | 16:30 | Not started |
| Audio, video, and screen share tested with speakers | Host | 16:45 | Not started |
| Admit attendees from the waiting room; pin the holding screen | Organizer | 16:45 | Not started |
| Holding screen up; speaker-timings note ready | Co-organizer | 17:00 | Not started |
| Start the recording | Host | 17:15 | Not started |
| Co-host watching the chat / Q&A queue | Co-organizer | 17:20 | Not started |
| Doors open: welcome + intros in the chat | Everyone | 17:30 | Not started |
| Why we’re here (community intro + theme) | Organizer | 18:00 | Not started |
| Talk one — keep time with the timings note | Speaker | 18:05 | Not started |
| Demos × 3 (5 min each) | Demo host | 18:30 | Not started |
| Wrap up — next event plug, group screenshot | Organizer | 18:55 | Not started |
| Social pulse — open networking in chat / breakouts | Everyone | 19:00 | Not started |

## NEXT DAY   Jun 25

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Thank speakers; collect slides to share | Organizer | Jun 25 | Not started |
| Thank co-hosts and any members who helped | Organizer | Jun 25 | Not started |
| Post the recap on LinkedIn with photos (Resources → recap) | Co-organizer | Jun 25 | Not started |
| Upload the recording + decks to the shared drive | Co-organizer | Jun 25 | Not started |
| Note final attendance vs RSVPs | Organizer | Jun 25 | Not started |

## FOLLOW-UPS   by Jun 30 · within a week

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Share recording / slides / demo links with attendees via Luma | Co-organizer | Jun 27 | Not started |
| Send the post-event feedback ask | Organizer | Jun 27 | Not started |
| Capture lessons learned here — what to change next time | Organizer | Jun 30 | Not started |
| Add interested attendees + speakers to the pipeline | Organizer | Jun 30 | Not started |
| Tee up the next event’s date (“AI in Finance” — Jul 22) | Local champs | Jun 30 | Not started |